## bugs
Bug List
# | Reported Date | Reported By | Severity [P0-P5] | Status [open, in-progress, resolved, won't fix] | Assigned To | Short Desc. | Expected Results | Actual Results | Steps to reproduce
1 | 2024-10-10 | Malcolm | P4 | in-progress | Malcolm | Holding down the shooting keys is not possible, as different keys overwrites each other. | Players continuously shoot while holding down the shoot button, and can move around while shooting | Players continuously shoot while holding down the shoot button, but pressing another button causes them to stop shooting | hold down the shoot button of either player. They will continuously shoot. Now, either player can move/shoot and the shooting from the first player will halt | Fixed
2 | 2024-10-13 | Edward | P5 | in-progress | Edward | Movement speed is different on different systems. On Edward's system, the horizontal movement is much slower than on the other systems. | Player's horizontal movements have the same speed across all systems; | On Edward's system, the horizontal movement is much slower than on the other systems. | Copy Edward's setup or run on his PC | Fixed
3 | 2024-12-02 | Edward | P5 | not fixed | Malcolm | Shooting buckshot then press R may cause some stages to be gone | all statges should be there whenever R is pressed | as per description | as per description

## bug_severities
Severity | Description
P0 | crash bug; game crashes and is unrecoverable
P1 | game stopping bug, but no crash; cannot keep playing
P2 | serious, game not working as expected
P3 | annoying, could ship but loss of marks
P4 | annoying or limiting, but could be shipped as-is
P5 | minor or feature that nice to have but could ship in future release